## PI1 SP2
Task Distribution
Milestone
Developers | SP | [5 empty] | UI enhancement should be the same us Figma
Asmerom | 5 | [5 empty] | Questions must work properly (selection, saving, checking, result)
Esrom B | 5 |  |  | Total Capacity | 160 | SP | Missed question should be retrieved and showed to user
Esrom T | 5 |  |  | Total Load | 50 | SP | Save user selection
Hani | 6 |  |  | Velocity | 128 |  | User authentication must be implemented
Kidane | 6 |  |  | Number of tasks | 34 |  | Navigation should be by auto route
Miki | 7 | [5 empty] | Complete flow chart
Mohammed | 4
Naod | 7
Yoel | 5
TOTAL SP | 50
|  | Capacity | 640 | hr
|  | Total SP Capacity | 160 | SP
|  | No of Tasks | 8
|  | Meeting hrs | 32
|  | Total Velocity | 128
|  | Load/ total SP | 200 | 50